## Version Control
Last updated | Version number | Change notes
2014-07-25 | 2 | Updated to reflect the notes from a meeting with alasdair, nick, infotech, udc on the data model.
2014-08-07 | 3 | Captured information on the info.
2014-08-20 | 4 | Udated with notes from meeting on capturing san francisco
2014-08-21 | 5 | Updated with issue from 8/20 Data Conversion meeting
2014-08-28 | 6 | Updated list to include additional items and reflect current state; Also added additional columns and a second tab for non-bay items
2014-08-29 | 7 | Updated with TFS numbers for most items in the list
2014-09-03 | 8 | Updated with rest of TFS numbers, formatting, added open/closed column and filtered on it. Filled in all missing data, updated information in each row
2014-09-03 | 9 | Updates to status on a few items, removed a column
2014-09-05 | 10 | Updates from Dayakar on necessity of non-Bay items
2014-09-05 | 10.1 | Updates from John Kelly on DSM status
2014-09-08 | 10.2 | Changed a few incorrect DA issue numbers
2014-09-08 | 11 | Added new PAR-based issue from Jo

## Bay Area DM Issues
Issue | Description | DA# | PAR# | Open/Closed | Model Version | Release Date | Status | Model Updated | Stored Displays Updated | App Code Updated | Conv Spec Updated | Delivered to Cyient | Model Change Type | Notes
Cross Section for Ducts | When you have an abandoned duct or abandoned cable in a duct. How does this work with the cross section anno in UFM? | 16552 | N/A | Closed | 9 | TBD | Implemented | N/A | Yes | Yes | Yes | No | #1 is 50 scale stored display #2 Change to Conductor Anno AU #3 | Deactivated electic line segment and deactivated conduit #1 change the size to cross hatch layer will be 1.8 in total. #2 DEACT is needed for conduit and for conductor annotation for "DEACT 3''" #3 cross section takes takes care of cross section objects. check with Roger that the AU for Cross Section will update the appropriate conduit symbol when a related conductor is deactivated
PAR #61652 -- T-Connector (Open Point Subtype) | Based on the communication with the SFO Mapping staff (see below from Charles Bandi and attached from Stephen Medina) and review of the issue by Jason Bright, on behalf of Jason, please create a TFS ticket for the creation of a new Open Point subtype with its corresponding symbol. Jason requests that this be discussed at the Wednesday DA meeting, but if the agenda is already too crowded, it can be discussed at the 11:00 am Friday meeting. Jason’s search for an existing symbol standard revealed no results. However, there is a reference to these in a PG&E Construction Manual; Cutouts and Fuses for Underground Distribution Lines that Jason believes describes this feature. A screen shot from page 18: | 14560 | 61652 | Open | 9 | TBD | Approved | Yes | No | N/A | Yes | No | Triangle or arrow head as a symbology today. w/no limiter w/limiter added on w/limiter built in New subtype on Open Point | Feature Class: Open Point Subtype name: Splice SpliceType = Wye Symbology is a open dot. underground only use for connectivity Does it need a subtype for sec/pri differntiation?
4kV feature class | "Time cont & manual sw" found in source | 17045 | N/A | Open | 9 | TBD | Implemented | Yes | N/A | N/A | No | No | Add 5000 and 4000 V to "Street Light Voltage" domain. Assign this domain to sec oh conductor, subtype streetlight, streetlight transformer, and sec ug conductor.
Stored display symbol change - Interrupter, Sectionalizer, others | When trying to place Device Group symbols in congested areas with groups of 4+ conductors, it is difficult to place without overlap. If the device group is placed on the 3rd of a set of 5 conductors, it will overlap one or more conductors on either side of it. Therefore the Conversion team is having to "draw around" the Device Group symbol and create arcs to avoid overlap. The proposed solution is to make the Device Group symbols which are a problem smaller in size so that they fit inside the border of the two conductors neighboring. | 16591 | N/A | Open | 9 | TBD | Implemented | N/A | Yes | N/A | N/A | No | Need to add a new Device Group Type for the TGRAL. Stored display update to symbolize it
Symbol size for the source stitch point | Dayakar to provide sizes - need to make smaller | 17065 | N/A | Closed | 9 | TBD | Approved | N/A | N/A | N/A | N/A | No | Miscommunication. Source Stitch Point does not need to be made smaller. Can be closed.
Streetlights - Two On One Pole | Streetlight symbol is overlapping itself when there are two lamps, annotation is also appearing twice | 16512 | N/A | Closed | 9 | TBD | Approved | N/A | N/A | N/A | N/A | No | Will add small conductor between the two streetlights - data change only, no data model impact | need details on exact error and workflow that caused this issue, we need the par for this if possible. Proposed solution is to draw small conductor between two streetlights - no data model change based on this solution.
Individual Light (IL) Transformers on SFO Block Maps | The symbol stands for "Individual Light Transformer" which is already included in the street light category of the legend for San Francisco UG map symbols. Uncertain if such mini transformers continue to exist and function in field, since SLs on Grant Ave. south of Broadway were already converted to 120V. Little is known about such transformers of the past with their connections to the supply source and the output voltage on the secondary side. To ascertain the connectivity to the 2-10S SL conductors, Mapping cannot offer solution without direct field verifications. | 16977 | 67224 | Open | 9 | TBD | DA | N/A | No | N/A | Yes | No | No model change. Stored display update required, still in DA | Per Ed Chan: I don’t think we continue to have many of these ‘legacy’ devices in our UG SL system in San Francisco. Chances are that the ones which you have seen may have already been disconnected from the source of feed or removed from field, except that Mapping needs field verification of their non-existence. I have no exact idea on how these ‘ILs’ work, or how the internal wirings of such SLs served would look like, except that the ILs are miniature spot transformers with source from probably an existing secondary to power a group of SLs of undetermined distance, or they may draw power from an R.O. loop as the source, and convert to 120V in order to feed a group of SLs.
Add support for offset placement of UFM floors | In dense areas, UFM butterfly diagrams will overlap one another if drawn in place. Under these conditions, one will be drawn at the correct location and others will be offset to a location where enough whitespace is available. However, since UFM floors are shown in both duct view and buttefly view, we need a flag for the Stored Display to know when to show one or the other. | 17049 | N/A | Open | 9 | TBD | DA | Yes | N/A | N/A | No | No | Conv spec to be updated | UFM Floor Type attribute with domain of "Duct View", "Butterfly View" and "All Views"
Customer Agreement Number - Issue With Capturing Data | There are cases where we have multiple Customer Agreements associated with a feature. There are many in SF where the same features have MLX numbers and Applicant Trench numbers. There can be cases where we have MLX and Special Facilities agreements as well, though Cyient hasn’t brought these forward. | 14355 | N/A | Closed | 9 | TBD | Approved |  |  |  | N/A |  | To be done by PG&E IT, can be closed from the perspective of this spreadsheet | Approved as long as the relationship is built on GUID. Impact to Conversion is that the data will need to be moved. Impact to existing Central Valley / Central Coast is that the relationship will need to be re-determined. Create a relationship Class which is a Table and populate with the GUID. Remove the foreign key GUID on each of the Feature Classes. PROD scripts will be specified and developed by PGE IT. PGE IT will also make the scripts available to IBM to execute in Conversion. CustAgreement_DeliveryPoint, CustAgreement_PadmountStruct, CustAgreement_PriOHCond, CustAgreement_PriUGCond, CustAgreement_SecOH, CustAgreement_SecUGCond, CustAgreement_ServiceLocation, CustAgreement_SubsurfaceStruct, CustAgreement_SupportStruct, CustAgreement_Transformer needs to be Many-to-Many
New Symbols Found - RO Loop SL Symbols | Multiple symbols have been found that are not currently represented in the data model. Need to symbolize each of these, details in DA TFS and 'Notes' column | 17198 | 67930 | Closed | 9 | TBD | Approved | N/A | N/A | N/A | N/A | N/A | No change required - capture as "Regulated Output Streetlight Transformer" | Although these symbols are in "AppendixNSFO_OAK_Historical_UG_MappingSymbols.pdf" document they are not currently represented/symbolized in GIS Conversion. Symbols at issue in this PAR are: · 'Regulating Outdoor Transformer (Circle with R.O. is the 30KW RO transformer for the RO Loop 561) · "TIME CLOCK" symbol (Connected to Secondary) · And the (middle symbol in the middle resembling a joint pole is the "Magnetic Control" (size unknown) How should these symbols for this MH 5320 location be captured for GIS Conversion?
TGRAM | Device Group type - TGRAM/TGRAL - needs to be smaller. Stored display symbology change | 17048 | N/A | Closed | 9 | TBD | Duplicate | [5 empty] | Covered by CR16591, Stored display symbol change
Block Maps with Cross Section | When we have cross section detail with notes made on them, we need to be able to capture the note info. | 16513 | N/A | Closed | 9 | TBD | Duplicate |  |  |  | Yes |  |  | Duplicate of "Add Note1/Note2 fields to VaultPoly"
Data Model: Add Conductor Change subtype for 1:50 for Open Points | Need to change the scale of conductor change subtype and then accounts for it in the 50 scale maps. Decision made to update the stored display. | 16153 | N/A | Closed | 9 | TBD | Duplicate |  |  |  | N/A |  | Duplicate of "Add Smaller Conductor Change Size Symbol for Downtown SFO/OAK"
Abandoned Conduit/Duct Bank are indicated in several ways | Cross hatch symbol, 'ABA'/'DEACT' text, Material/DuctSize/MeasuredLength are captured on new feature class, DeactivatedIDC=Yes, leave DuctsFilled/DuctsVacant/VacantIDC=null, Available=Unavailable, Status=30 (idle). DuctBank is a crosshatch line with 'DEACT'. |  |  | Closed | 8.5.1 | 2014-08-30 | Duplicate |  |  |  | Yes |  |  | Deactivated electic line segment and deactivated conduit #1 change the size to cross hatch will be 1.8 in total. #2 DEACT is needed for conduit and for conductor annotation for "DEACT 3''" #3 cross section takes takes care of cross section objects. Duplicate of "Cross Section for Ducts"
Abandoned Conduit/Duct Bank are indicated in several ways | Duct has symbology for one conduit that is deactivated. Crosshatch. Does this mean 'conduit' or 'duct'? |  |  | Closed | N/A |  | Duplicate |  |  |  | Yes |  |  | Duplicate of "Cross Section for Ducts"
Abandoned Conduit/Duct Bank are indicated in several ways | Conduit - Crosshatch line, 'DEACT', 5' P annotation if this info exists |  |  | Closed | N/A |  | Duplicate |  |  |  | Yes |  |  | Duplicate of "Cross Section for Ducts"
Abandoned Conduit/Duct Bank are indicated in several ways | Symbology must be smaller for smaller scale areas - cross hatch marks could overlap other conductors if there are multiple conductors next to each other |  |  | Closed | N/A |  | Duplicate |  |  |  | Yes |  |  | Duplicate of "Cross Section for Ducts"
Add Smaller Conductor Change Size Symbol for Downtown SFO/OAK | The conductor change symbol is currently based on a 4’ offset of the conductors. In this example in downtown SFO, given the amount of conductors, the offset of the cables was reduce d to 1’ – we therefore need a smaller symbol so that it doesn’t overlap the other conductors. | 16164 | N/A | Closed | 9 | TBD | Implemented | N/A | Yes | N/A | N/A | No | 50 scale stored display change | conductor change, OPENPOINT 1.8 SIZE FOR ALL SYMBOLS MADE IN THE STORED DISPLAY in underground
4kV Junction Node, Hexagonal | New junction with 5 incoming lines splitting the space into a hexagon. Need to symbolize this | 16308 | 61453 | Closed | 9 | TBD | Implemented | Yes | Yes | N/A | Yes | No | Domain value change Stored display update | Need a new symbol in the fonts or need to idenitify which one of the existing to us. Need an update and confirmation from Eric Rodgers. Then need a conversion process identified for current data Then need symbol number AU updated to reflect Then need new stored display layer update.
Load Point to Service Location | In this region, we have an additional tier. It is normally xfmr->service loc->service pt. Now it is xfmr->load point->service loc->service pt | 16514 | N/A | Closed | 9 | TBD | Implemented | Yes | N/A | N/A | N/A | No | New relationship classes between XFMR/SLP (1:M) and SLP/SL (1:M) | Already existing converted data for downtown does not have load points, so we cannot create/use the feature. No symbology exists. Solution described was to add a subtype to service location with relationships to network transformers for this specific case. Need a name for the Service Location subtype. No solution exists for tracing network features in a mesh network using ArcFM Feeder Manager. Cases exist in which the correct load point upstream from a service location cannot be determined by written logic
Conductor Cross Section Annotation | Need to minimize content for better white space management | 17202 |  | Closed | 9 |  | Implemented | Yes | N/A | Yes | Yes | No |  | Eliminate UNK's; Remove "PX" from conductor type; Modify operating voltage to eliminate decimal places and the space between value and unit (kV)
One phase dead cable | Secondary conductor. 3 phase triplex cable but we're only using two hot legs. One phase is dead - we need to show this on the maps. Symbology? Subtype? Annotation/rules? | 16511 | 68517, 68762 | Closed | 9 | TBD | Implemented | Yes | N/A | Yes | Yes | No | Add field DEADPHASEIDC to SecUGConductorInfo Update labeltext expression for anno to append "Dead <phi>" | In the TFS 16511 , next data model release Business agrees that there is no white space management issue for Central Coast and Central Value. Solution in Specs is: On the Secondary Panel of a Block Map, when a note; “3 ϕ LEG DEAD” or “ONE LEG DEAD” is encountered on a Three Phase Secondary Underground, create a record in the SecUGConductorConductor Info table and set the DeadPhaseIdc field to ‘Yes’. This same designation can also occur on the Duct Bank configuration/”cross-section” panel. This is only applicable to the Three Phase Secondary Underground subtype. When this field is set to ‘Yes’, the annotation expression will include the rendering “DEAD ϕ”.
3-Way Ties in SFO Block Maps | Need a feature defined for capturing the "3-Way Ties" that appear on the SFO Block Maps. This originated from John Kelly as a result of finding it on a Block Map. This is not the same as the "T-Connector" issue above. See example. | 16596, 16698 | N/A | Closed | 9 | TBD | Implemented | Yes | N/A | N/A | Yes | No | New subtype for Tie feature class Rename existing subtype on Tie | Resolved via the TFS tickets. Implemented in DSM and Specs. Needs to be implemented in data model and elsewhere as required.
Tie cables/network cables | How do we differentiate between tie cables, network cables, and radial cables? This issue applies to both the primary and secondary networks. Currently all three features are symbolized with the same symbol, but we need to be able to differentiate on a printed map what each of these are. | 16510 | N/A | Closed | 9 | TBD | Implemented | Yes | N/A | N/A | Yes | No | New field, FEEDERTYPE on CircuitSource; New domain for above field | Add a new field to capture the FEEDERTYPE So far we know we must have conductors, but question is also around other devices Domain of Feeder Type valus of only: 1 : Tie 2 : Network 3 : Radial 4: Substation Data Conversion not in the provided list then set it to Substation
Add support to place Neutral Conductor lines in ducts | Numerous examples of neutral conductors running alone in ducts have been encountered in the source maps. They can not be associated with a particular primary or secondary conductor and the model doesn't currently support running Neutral conductor through a duct. Revise to add support. | 17041 | N/A | Closed | 9 | TBD | Implemented | Yes | N/A | N/A | N/A | No | Add relationship classes and AU's | 1) Create Relationship Class Conduit_NeutralConductor 2) Apply AU’s to the Conduit_NeutralConductor relationship class 3) Create Relationship Class NeutralConductor_Duct 4) Apply AU’s to the NeutralConductor_Duct relationship class. Details in TFS
Masking vaults | UFM tools in ArcFM need lines to tie into a center point to keep connectivity. However it goes through a vault and through a substation in real life. Need to create a vault mask feature to hide the extra lines | 17042 | N/A | Closed | 9 | TBD | Implemented | N/A | N/A | N/A | N/A | No | No change required | This is being managed through the draw order (conductor lines over vault polygon/UFM floor over conduit)
Position Description Needs to Exist on Device Group | For now position description is on the transformer and not the device group. The IVARA data model we are intergarting to through SAP needs this to exist on the device group. Conversion team would like this change put into a data model release for down town. IVARA data model change needed for conversion to implement. DA decision made, data model change is documented. Need ? What in this meeting again? | 16529 | N/A | Closed | 9 | TBD | Implemented | Yes | N/A | N/A | Yes | No | Fields and data model changing. | 1) We will be adding the PositionDescription attribute to the Device Group feature class Attribute: POSITIONDESCRIPTION Alias: Position Description DataType: Text Size: 50 No Domain Visible Editable 2) We will be removing POSITIONDESCRIPTION from TransformerUnit 3) We will be removing the relationship between Transformer and Switch (deferred to another ticket) 4) We will be removing the relationship between Transformer and NetworkProtector (deferred to another ticket) 5) We will be creating a relationship between DeviceGroup and and the NetworkProtector
VaultPoly Extra Fields | Need Note1 and Note2 fields on the VaultPoly. Will need an AU (or something else) in some cases to populate the Note1 and Note2 from the VaultFloor | 17046 | N/A | Closed | 9 |  | Implemented | N/A | N/A | N/A | Yes | No | Already implemented in an earlier release
DA Issue: Add Leader Line Feature | In a location with conductor anno that is very tight, we need to be able to have leader lines so we can offset the annotation to a location that is clearer | 15795, 16536 | N/A | Closed | 8.5.1 | 2014-07-30 | Implemented | Yes | ? | N/A | Yes | Yes | New feature class | Confirmed all leader line usage in email from Rob is correct. Further clarification on usage when lines are intersecting others and at angles.
PAR 64063: Transformer Overstriking in SFO | Pole with a Transformer on a line. Offset is fixed for transformer from line. But in SF, Transformer may overlap lines if multiple lines on the same pole. Need to offset features by a variable amount, esp. transformers. | 16491 | 64063 | Closed | 8.5.1 | 2014-07-30 | Implemented | Yes | ? | N/A | Yes | Yes | Additional symbols in font new domain (1,2,3) new field on transformer add new symbols into MXD | Field: SymbolSpace values 1,2,3 will cause the MXD layers to show with a spacing equvalent to default * 1,2,3 to account for more lines. This effects All overhead transformer sybtypes , everything else set to not applicable. Need a Domain with the 1,2,3 range Re-Configure the symbol au so that it moves these out, change the MXD and then space theses out multiplier. Other feature types will be handled with shrinking of the symbol sizes.

## Non-Bay DM Issues (Approved)
ID | Title | Assigned To | State | Changed By | Changed Date | Comment | Dayakar's comments
8847 | Open/Closed Switch Annotation - Circuit Map (7.X) | Peaslee, Don | Active | Peaslee, Don | 2014-07-23 14:23 | Part of original 8.6 list but not delivered by Dev | No. Impacts whitespace management, not requested by Cyient
10594 | Change Netural Conductor Annotation Expression (Special Case - Requires impact analysis w/ existing work: TBD) | Jasicki, Richard | Active | Peaslee, Don | 2014-07-23 14:23 | Part of original 8.6 list but not delivered by Dev | Yes, but change. All fields are on feature class, label expression is sufficient instead of AU
11671 | ArcFM field properties changes (DM TBD-WEBR 2.0: DEV TO ANALYZE-DEB TO OWN) | Nadar, George Raja | Active | Narasimham, Ashish | 2014-05-20 17:34 | Part of original 8.6 list but not delivered by Dev | No. Not needed for conversion
13154 | SSL annotation for under ground secondary conductor | Jasicki, Richard | Proposed | Peaslee, Don | 2014-07-23 14:23 | Part of original 8.6 list but not delivered by Dev | Yes. Model change, AU change
13580 | Ground Switch Fields | Jasicki, Richard | Active | Peaslee, Don | 2014-07-23 16:00 | Part of original 8.6 list but not delivered by Dev | Yes, Add fields to TransformerDevice
13832 | Create New Feature Class for Antenna | Uyema, Michael | Active | Peaslee, Don | 2014-07-23 16:26 | Part of original 8.6 list but not delivered by Dev
13834 | setup symbology for Antenna | Jasicki, Richard | Proposed | Peaslee, Don | 2014-07-24 | Don attached to 14830 (DM 8.6 Candidate list). Does not appear to have gone though DM Meeting. | Yes
14249 | Add New Value to Conductor Type - UG Domain PAR #57706 | Jasicki, Richard | Active | Kelly, John M | 2014-07-23 16:00 | Part of original 8.6 list but not delivered by Dev | yes
14452 | Connectivity rule - Secondary OH Conductor connected to a Trasnformer Tie via a Streetlight | Jasicki, Richard | Proposed | Narasimham, Ashish | 2014-05-20 18:03 | Part of original 8.6 list but not delivered by Dev | No. Not urgent
14895 | Add New Value to Secondary Voltage Domain - PAR #60673 | Jasicki, Richard | Active | Uyema, Michael | 2014-08-27 15:56 | Part of original 8.6 list but not delivered by Dev | Yes
14901 | DA Issue :Moving a pole with a riser attached, the riser is moving with it | Jasicki, Richard | Proposed | Jasicki, Richard | 2014-07-18 10:37 |  | No
15064 | EDGIS Data Model Changes for TLM | Jasicki, Richard | Active | Jasicki, Richard | 2014-08-22 12:32 |  | Yes
15898 | WP 27/28 Add COR and PTT to Joint Pole Members Domain | Jasicki, Richard | Active | Jasicki, Richard | 2014-07-18 10:44 |  | no
16229 | DA Issue: Remove Structure Size domain from Vault Subtype | Jasicki, Richard | Active | Jasicki, Richard | 2014-07-18 11:20 |  | no
16309 | Add DuctCount attribute to PGEDuctDefinition table | Jasicki, Richard | Active | Jasicki, Richard | 2014-07-18 11:48 |  | yes
16596 | Add new Subtype "Mesh Tie" to Tie Feature Class | Jasicki, Richard | Proposed | Jasicki, Richard | 2014-08-07 10:31 |  | DUPLICATE
16698 | DM Change to EDGIS.Tie | Jasicki, Richard | Active | Jasicki, Richard | 2014-08-12 08:44 |  | DUPLICATE
17014 | PAR 71520: Add Values 25 - 40 to Conductor Count Domain | Uyema, Michael | Active | Jasicki, Richard | 2014-08-27 13:34 |  | yes
*These Tickets attached to CR7489 Future 1.1 DM Release
7304 | Landbase requested removals from landbase team. | Narasinham, Ashish | Proposed | Uyema, Michael | 2014-08-27 | On Hold per Ashish | No
7339 | Drop and re-add field to fix spelling: SUBLoadTapChanger field name TAPLIMITERACTIVE | Narasinham, Ashish | Active | Uyema, Michael | 2014-08-27 | On Hold per Ashish | No
7340 | Drop and re-add field to fix spelling: SUBLoadTapChanger field name TAPLIMITERHIGHSETTING | Narasinham, Ashish | Active | Uyema, Michael | 2014-08-27 | On Hold per Ashish | No
7341 | Drop and re-add field to fix spelling: SUBLoadTapChanger field name TAPLIMITERLOWSETTING | Narasinham, Ashish | Active | Uyema, Michael | 2014-08-27 | On Hold per Ashish | No
7967 | PAR 20907: Distribution Subsurface Transformer Device Group Structure Type Name Not In Drop Down | Narasinham, Ashish | Active | Uyema, Michael | 2014-08-27 | On Hold per Ashish | Yes